# Pilot Protocol & Operational Deployment Plan

Document Reference: CAW-PILOT-PROT-2026-01
System: Case Ace v2.0 Client Consultation Recording & Note Drafting System
Organisation: Citizens Advice Wandsworth (CAW)
Target Bureau Cohorts: Battersea Bureau, Roehampton Outreach, and Central Telephony
Duration: 6 Weeks (October 12, 2026 – November 20, 2026)
Sample Target: 15 Generalist Advisers, Minimum 250 Live Advice Consultations
Status: Formally Approved Pilot Protocol
Classification: Internal / Operational Pilot

## 1. Pilot Purpose & Strategic Objectives

The primary objective of the Case Ace v2.0 pilot is to evaluate the real-world operational feasibility, note quality, privacy preservation, and adviser experience of assistive case note drafting in live advice environments.

flowchart LR A["Week 1: Adviser Training & Baseline"] --> B["Weeks 2-3: Supervised Pilot (100% QA)"] B --> C["Weeks 4-5: Steady Pilot (10% QA + Survey)"] C --> D["Week 6: Evaluation & Board Decision"]

## 2. Pilot Cohort & Sample Size

+----------------------------------------------------------------------------------------------------+ ¦ PILOT PARTICIPANT COHORT BREAKDOWN ¦ +----------------------------------------------------------------------------------------------------+ ¦ Advice Channel ¦ Adviser Cohort Size ¦ Target Consultations (6 Weeks) ¦ +----------------------------------------------------------------------------------------------------+ ¦ **In-Person Consultations**¦ 6 Generalist Advisers ¦ 110 Consultations (Battersea / Roehampton) ¦ ¦ **Webex Telephony** ¦ 5 Adviceline Advisers ¦ 100 Consultations (Wandsworth Hub) ¦ ¦ **Outreach / Home Visits** ¦ 4 Specialist Caseworkers ¦ 40 Consultations (Dictaphone Import) ¦ ¦ **Total Pilot Scope** ¦ **15 Qualified Advisers** ¦ **250 Validated Consultations** ¦ +----------------------------------------------------------------------------------------------------+

### Participant Selection Criteria:

- Mixture of full-time caseworkers, part-time generalist advisers, and experienced volunteer advisers.

- Representation across core advice categories: Welfare Benefits & Universal Credit (40%), Debt & Money (25%), Housing & Homelessness (20%), Employment & Energy (15%).

## 3. Phased 6-Week Pilot Timeline

### Phase 1: Preparation & Training (Week 1)

- Comprehensive 3-hour hands-on training for all 15 participating advisers.

- Practice with synthetic scenarios, Review Gate editing, and Easy-Read consent delivery.

- Baseline measurement of manual note-taking duration (average time spent per consultation without Case Ace).

### Phase 2: High-Supervision Live Rollout (Weeks 2–3)

- Live consultations begin with Case Ace assistance.

- 100% Supervisory QA: Every case note drafted with Case Ace is reviewed by a Lead Supervisor before formal case file closure in Casebook CRM.

- Daily 15-minute operational standups with IT support to resolve minor UI friction.

### Phase 3: Steady-State Operations (Weeks 4–5)

- Transition to standard 10% random supervisory sampling.

- Intermediate telemetry review (monitoring latency, override frequency, and gap acknowledgments).

- Client exit surveys administered to consenting clients.

### Phase 4: Formal Evaluation & Governance Review (Week 6)

- Data aggregation against the Evaluation Framework (AQS quality scores, time savings, redaction precision).

- Independent review by CAW Data Protection Officer and Quality Lead.

- Final recommendation report submitted to the CAW Board of Trustees.

## 4. Operational Support and Safety Safeguards

1. Dedicated On-Call Technical Support: IT support is reachable on internal extension 4567 throughout all clinic hours.

2. Instant Fallback: Advisers retain complete autonomy to revert to standard manual note-taking at any time.

3. Daily Data Protection Monitoring: DPO reviews audit log health every morning to confirm zero anomalies.